## ProjectPlan
PROJECT TITLE | [57 empty] | [42]
[Company Name] | [9 empty] | © 2017 by Vertex42.com
[Project Lead] |  |  | Project Start: | 2022-03-14
|  |  | Display: | Weekly
|  |  | Display Period: | 1 | time axis 2022-03-14 to 2023-03-27
[10 empty] | 14 Mar '22 | 21 Mar '22 | 28 Mar '22 | 4 Apr '22 | 11 Apr '22 | 18 Apr '22 | 25 Apr '22 | 2 May '22 | 9 May '22 | 16 May '22 | 23 May '22 | 30 May '22 | 6 Jun '22 | 13 Jun '22 | 20 Jun '22 | 27 Jun '22 | 4 Jul '22 | 11 Jul '22 | 18 Jul '22 | 25 Jul '22 | 1 Aug '22 | 8 Aug '22 | 15 Aug '22 | 22 Aug '22 | 29 Aug '22 | 5 Sep '22 | 12 Sep '22 | 19 Sep '22 | 26 Sep '22 | 3 Oct '22 | 10 Oct '22 | 17 Oct '22 | 24 Oct '22 | 31 Oct '22 | 7 Nov '22 | 14 Nov '22 | 21 Nov '22 | 28 Nov '22 | 5 Dec '22 | 12 Dec '22 | 19 Dec '22 | 26 Dec '22 | 2 Jan '23 | 9 Jan '23 | 16 Jan '23 | 23 Jan '23 | 30 Jan '23 | 6 Feb '23 | 13 Feb '23 | 20 Feb '23 | 27 Feb '23 | 6 Mar '23 | 13 Mar '23 | 20 Mar '23 | 27 Mar '23
WBS | TASK DESCRIPTION | ASSIGNED TO | PROGRESS | PLAN START | PLAN END | PLAN DAYS | ACTUAL START | ACTUAL END | ACTUAL DAYS | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54
| Gian Đoạn 1 (Giới Thiệu) |  | 85% | 2022-03-14 | 2022-04-04 | 22
1 | Viết Giới Thiệu | Tất Cả | 80% | 2022-03-14 | 2022-03-24 | 11
2 | Tổng Hợp Chức Năng | Tất Cả | 90% | 2022-03-24 | 2022-04-03 | 11
3 | Báo Cáo |  |  | 2022-04-04 | 2022-04-04 | 1
| Gian Đoạn 2 (Thiết Kế và Cài Đặt) |  |  | 2022-04-04 | 2022-04-24 | 21
3 | Thiết Kế Database | Phùng và Hiển | 80% | 2022-04-04 | 2022-04-24 | 21
4 | Cài Đặt Môi Trường FrontEnd | Hiển | 90% | 2022-04-04 | 2022-04-24 | 21
5 | Cài Đặt Môi Trường BackEnd | Phùng | 70% | 2022-04-04 | 2022-04-24 | 21
6 | Tạo Entities từ Database | Hiển | 100% | 2022-04-04 | 2022-04-24 | 21
7 | Vẽ Class Diagram | Tường | 100% | 2022-04-04 | 2022-04-24 | 21
8 | Vẽ Database Diagram | Khánh | 100% | 2022-04-04 | 2022-04-24 | 21
9 | Quy Tắc Chung Giao Diện | Duy | 100% | 2022-04-04 | 2022-04-24 | 21
10 | Báo Cáo |  |  | 2022-04-25 | 2022-04-25 | 1
| Gian Đoạn 3 (Chức Năng) |  |  | 2022-04-25 | 2022-05-15 | 21
11 | Đăng Nhập với JWT | Phùng | 100% | 2022-04-25 | 2022-05-15 | 21
12 | Đăng Ký học phần sinh viên | Hiển | 100% | 2022-04-25 | 2022-05-15 | 21
13 | Đăng Ký lớp giáo viên | Tường | 100% | 2022-04-25 | 2022-05-15 | 21
14 | Xem Học Phí | Khánh | 50% | 2022-04-25 | 2022-05-15 | 21
14 | Xem Lịch Thi | Duy | 50% | 2022-04-25 | 2022-05-15 | 21
15 | Báo Cáo |  |  | 2022-05-16 | 2022-05-16 | 1
| Gian Đoạn 4 (Chức Năng) |  |  | 2022-05-16 | 2022-06-05 | 21
16 | Quản Lý Entities | Phùng | 100% | 2022-05-16 | 2022-06-05 | 21
17 | Thêm Học Viên Tự Động | Hiển | 100% | 2022-05-16 | 2022-06-05 | 21
18 | Xem điểm | Tường | 100% | 2022-05-16 | 2022-06-05 | 21
19 | Xem Thông Tin Giáo viên | Khánh | 0% | 2022-05-16 | 2022-06-05 | 21
20 | Xem thời khóa biểu | Duy | 100% | 2022-05-16 | 2022-06-05 | 21
21 | Báo Cáo |  |  | 2022-06-06 | 2022-06-06 | 1
| Gian Đoạn 5 (Chức Năng) |  |  | 2022-06-06 | 2022-06-26 | 21
22 | Thêm Điểm Tự Động | Phùng | 100% | 2022-06-06 | 2022-06-26 | 21
23 | Tra Cứu Thông Tin Tốt Ngiệp | Hiển | 0% | 2022-06-06 | 2022-06-26 | 21
24 | Kết Thúc Đăng Ký | Tường | 0% | 2022-06-06 | 2022-06-26 | 21
25 | Xem Chương Trình Đào Tạo | Khánh | 0% | 2022-06-06 | 2022-06-26 | 21
26 | Quên Mật Khẩu | Duy | 100% | 2022-06-06 | 2022-06-26 | 21
27 | Báo Cáo |  |  | 2022-06-27 | 2022-06-27 | 1
| Gian Đoạn 6 (Phát Sinh) |  |  | 0 | 1900-01-19 | 21
28 | Biểu Đồ |  | 100% | 0 | 1900-01-19 | 21
29 | Thông báo |  | 100% | 0 | 1900-01-19 | 21
33 | Báo Cáo |  |  | 1900-01-20 | 1900-01-20 | 1

## Help
HELP
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
About
This project planner template was designed to provide a simple way to create a project schedule with a Gantt chart that shows both planned and actual dates. Other than that, it contains very few features, which may be great if you want something simple.
Want more features?
Learn About Gantt Chart Template Pro
Adding More Rows
When you insert new rows, you should insert a blank row between rows that have the formatting you want. If you do that, the formatting will be copied automatically.
Text Within the Gantt Chart
You can enter text within the gantt chart area, but that text does not move if you adjust the start/end dates or use the scroll bar.
Adding More Columns to the Gantt Chart
If you want to increase the time span shown in chart, you can add columns to the right of the Gantt chart by copying and pasting entire columns.
Conditional Formatting
The bars of the Gantt chart are created using conditional formatting. This spreadsheet is not designed to allow you to change the colors for different bars. Use Gantt Chart Pro if you want to do that.
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
Other Templates
Visit Vertex42.com to find other project management templates.
Project Management Templates

## ©
Project Planner Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/project-planner-template.html
© 2017 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet.